## Bug Report
DEMOBLAZE - BUG REPORT
PRODUCT NAME | Demoblaze
CREATED BY | Saman Iftikhar
CREATION DATE | 2026-03-16
ENVIRONMENT | Web
BROWSER | Chrome
VERSION | Latest stable release (as of testing date)
Bug ID | Module | Bug Description | Steps to Reproduce | Test Data | Actual Result | Expected Result | Classification | Severity | Priority | Status | Screenshot
BUG_001 | Signup | Previously entered field values remain populated in the Sign Up form after it is closed and reopened. | 1. Go to the Sign Up form. 2. Enter a name and password. 3. Click Sign Up. 4. Click Close. 5. Reopen the Sign Up form. | Username: samna124 Password: -2 | Fields remain populated with previously entered data. | Fields should be empty when the form is reopened. | Potential Bug / Usability | Low | Low | Open
BUG_002 | Signup | Name field accepts a purely numeric value with no format validation. | 1. Go to the Sign Up form. 2. Enter a numeric-only value in the Name field. 3. Enter a valid password. 4. Click Sign Up. | Username: 1996 Password: -12 | Signup succeeds with a fully numeric name. | Name field should validate for alphabetic input, consistent with conventional name-field behavior. (Confirmed via testing: this is a usability observation, not a false 'already exists' error - that earlier assumption was disproved by retesting with guaranteed-unique values.) | Potential Bug / Usability | Low | Low | Open
BUG_003 | Signup | Password field accepts a single-digit numeric password with no minimum length validation. | 1. Go to the Sign Up form. 2. Enter a fresh, unique name. 3. Enter a single-digit password. 4. Click Sign Up. | Username: Hamza ali Password: 0 | Signup succeeds with a 1-character password. | System should enforce a minimum password length (e.g., reject passwords under 6-8 characters). | Confirmed Bug | Medium | Medium | Open
BUG_004 | Signup | Signup button is sometimes unresponsive after navigating away from and back to the site. | 1. Go to the Sign Up form. 2. Enter a name and password. 3. Navigate to another website. 4. Return to the Demoblaze signup page. 5. Click Sign Up. | Username: samna124 Password: -2 | Signup button becomes unresponsive. | Signup button should remain responsive regardless of navigation history. | Needs Further Investigation | Low | Low | Open
BUG_005 | Login | Entering an invalid username displays the same message as an invalid password ('invalid password'), rather than a generic combined message. | 1. Go to the Login form. 2. Enter a username that does not exist. 3. Enter any password. 4. Click Login. | Username: huzafa Password: -2 | System displays 'invalid password'. | This is likely intentional security behavior (prevents an attacker from confirming whether a username exists - 'username enumeration' protection), not a defect. If flagged, recommend only a wording refinement to a combined 'invalid username or password' message for clarity, not a functional fix. | Not a Bug | Low | Low | Closed - By Design
BUG_006 | Login | Login page does not provide a password recovery / 'Forgot Password' option. | 1. Go to the Login page. 2. Review available options. | Username: saman123 Password: forget | No password recovery option is present. | Consider adding a password recovery option for improved usability. | Enhancement | Low | Low | Suggestion
BUG_007 | Place Order | System does not validate whether the cart contains any items before allowing an order to be placed. As long as all required form fields (name, country, city, credit card, month, year) are correctly filled in, an order confirmation with an order ID is generated - even if the cart is completely empty. | 1. Ensure the cart is empty (no products added). 2. Navigate directly to Place Order. 3. Fill in all required fields with valid data. 4. Click Purchase. | Cart: empty. Name: Saman, Country: Pakistan, City: Lahore, Card: 4111111111111111, Month: 08, Year: 2027 | Order confirmation is displayed with a generated order ID, despite the cart having zero items. (Note: field-level validation itself works correctly and consistently - empty required fields are correctly rejected whether the cart is empty or has a product. The issue is specifically the missing cart-content check.) | System should verify the cart contains at least one product before allowing the order to proceed, regardless of whether the form fields are filled in correctly. | Confirmed Bug | High | High | Open
BUG_008 | Cart | Footer is not aligned with the bottom of the page on the Cart page, unlike other pages (e.g., Home). | 1. Open the Cart page. 2. Compare footer position with the Home page. | N/A | Footer is not aligned with the bottom. | Footer should remain consistently aligned across all pages. | Confirmed Bug | Low | Low | Open | Needed - add screenshot
BUG_009 | Place Order | Order form does not include a delivery Address field. | 1. Go to Cart. 2. Click Place Order. 3. Review the fields present on the form. | N/A | Order form only includes Name, Country, City, Card, Month, Year - no Address field. | Likely an intentional simplification for this demo site rather than a missing requirement, since Demoblaze does not process real shipments. | Not a Bug | Low | Low | Closed - By Design
BUG_010 | Contact Us | Contact form accepts submission with all fields left empty. | 1. Go to Contact Us. 2. Leave all fields (Email, Name, Message) empty. 3. Click Send Message. | Email: (empty) Name: (empty) Message: (empty) | System displays 'Message successfully sent' despite all fields being empty. | System should display a validation error (e.g., 'Please fill in all required fields') and block submission. | Confirmed Bug | High | High | Open
BUG_011 | Contact Us | Email field accepts an invalid (purely numeric) format with no validation. | 1. Go to Contact Us. 2. Enter a numeric-only value in the Email field. 3. Fill remaining fields. 4. Click Send Message. | Email: 123 Name: (empty) Message: (empty) | System accepts the numeric value as a valid email and confirms submission. | Email field should enforce a valid email format (e.g., must contain '@' and a domain). | Confirmed Bug | Medium | Medium | Open
BUG_012 | Contact Us | Name field accepts a purely numeric value with no format validation. | 1. Go to Contact Us. 2. Enter a numeric-only value in the Name field. 3. Fill remaining fields. 4. Click Send Message. | Email: saman@gmail.com Name: (numeric) Message: (empty) | System accepts the numeric value as a valid name. | Name field should enforce alphabetic format, consistent with conventional name-field behavior. | Potential Bug / Usability | Low | Low | Open
BUG_013 | Contact Us | Contact form accepts submission with the Message field left empty. | 1. Go to Contact Us. 2. Enter a valid Email and Name. 3. Leave the Message field empty. 4. Click Send Message. | Email: saman@gmail.com Name: saman Message: (empty) | System displays 'Message successfully sent' despite an empty Message field. | Message field should be marked required and block submission if empty. | Confirmed Bug | Medium | Medium | Open
BUG_014 | Place Order | Credit Card Number field has no format or length validation and accepts alphabetic characters. | 1. Go to Cart. 2. Click Place Order. 3. Enter alphabetic characters in the Credit Card Number field. 4. Fill remaining fields. 5. Click Purchase. | Name: saman Country: Pakistan Credit Card: abc | Order is accepted and confirmed despite an invalid, non-numeric card number. | System should enforce numeric format and minimum/maximum length validation on the Credit Card Number field. | Confirmed Bug | High | High | Open